## Tender
Housing Urban Development & Public Health Engineering Department Division Faisalabad
Construction of Child & PWD friendly School Toilet (4'x6') & (6'x6') at Government Girl's High school- 96-RB UC # 24 District Faisalabad
WORKDONE STATEMENT
Agreed Quantity/cost
Sr. | Description of work | Quantity | Unit | Unit Rate | Amount
1 | Excavation for foundation, underground tanks (rectangular or square), trenches and drains in all kinds of soil including rock and removing all vegetation alongwith their roots and back filling selected excavated material in foundation, plinth or under floor | 149.6533 | Cft
2 | Providing & laying 1:3:6 (1 cement 3 sand and 6 coarse aggregate) cement concrete using graded crush ¾ inch (20mm) and down gauge in foundation including levelling, compacting and curing, etc., complete. | 92.645 | Cft
3 | Providing & laying 1:2:4 (1 cement 2 sand and 4 coarse aggregate) cement concrete using graded crush ¾ inch (20mm) and down gauge in foundation including levelling, compacting and curing, etc., complete. | 12.5 | Cft
4 | Providing and laying first class solid burnt brick masonry set in cement mortar 1:4 in straight or curved walls 4-1/2" inches (114mm) and less in thickness including scaffolding, raking, out joints and curing, etc., complete in all floors. | 142.5177 | Cft
5 | Providing and laying first class solid burnt brick masonry set in cement mortar 1:5 in straight or curved walls 9" to 13-1/2 inches (228mm to 343mm) thick including scaffolding, raking out joints and curing, etc., complete in foundation, basement and plinth, & super structure all floors, including, all lead and lift. | 371.5058 | Cft
6 | Providing and laying DPC of 2 inch thick machine mixed 1:2:4 cement concrete using graded crushed boulders 3/4 inch (19 mm) and down gauge including form work, consolidation, finishing, curing etc., complete (a) with one coat of bitumen and one coat of polythene sheet 500 gauge :- | 31.83 | Cft
7 | Providing and laying machine mixed reinforced cement concrete using graded crushed boulders 3/4 inch (19mm) and down gauge having a minimum works cube crushing strength of 3000 lbs.per sq. inch(20 N/mm2) at 28 days with a mix not leaner than 1:2:4 including form work and its removal, compacting and curing, etc., but excluding the cost of reinforcement in all floors including all lead and lift. | 9.1562 | Cft
8 | Providing & laying mild steel reinforcement bars with minimum yield stress of 40,000 Psi with and including the cost of straightening, cutting, bending, binding, wastage, and such overlaps as are not shown over the drawings, placing in position on cement concrete 1:2:4 precast or M.S. chairs, tying with binding wire, cost of chair and wires, etc., in all kinds of RCC work in foundation, basement, plinth, ground, and all floors of building including septic tank, underground tank and in projections for future extension. | 12.9302 | Kg
9 | Providing and fixing 1'' thick Precaste RCC Plates for roof (having 1 bar of 2.54 mm (1 soot) MS steel around collor, with enforcing with one extra bar on sides, and two bars across center of plate horizetal and one vertical for (1.5'x4.5') plates (for 4'x5' toilet room) | 4 | Rft
10 | Providing and fixing 1'' thick Precaste RCC Plates for roof (having 1 bar of 5 mm (2 soot) MS steel around collor, with enforcing with one extra bar on sides, and three bars across center of plate horizetal and one vertical for (1.5'x6.5') plates (for 4'x6 toilet room) | 4 | nos
11 | Providing and laying 1.5 inch (40mm) thick machine mixed PCC in 1:2:4 cement concrete using graded crushed boulders 1/4 inch (6 mm) and down gauge over roof, finishing, curing etc complete in all respect (for 6'x4' toilet room) | 11.1281 | Cft
12 | Providing and laying coping of 1.5 inch (40mm) thick machine mixed 1:2:4 cement concrete using graded crushed boulders 3/4 inch (19mm) and down gauge in ground floor laid in panels including form work, consolidation, finishing, curing etc., complete | 17.1088 | sft
13 | Dry rammed Brick/Stone blast Under Floor mix with25%sand | 113.1625 | Cft
14 | Earth filling under floor | 108.4975 | Cft
15 | Providing and laying floor of 2 inch thick machine mixed 1:2:4 cement concrete using graded crushed boulders 3/4 inch (19 mm) and down gauge in ground floor laid in panels with marble dividers of 1/2"x2", consolidation, finishing, curing etc., complete | 310.15 | Cft
16 | Providing and laying 1.5'' (38 mm) thick layer of earth over roofs | 7.5 | Sft
17 | Providing and laying of 1/2'' (20 mm) thick mud plaster over roofs with bhusa (chuff not large 2 cm) @ 1kg / cft of earth | 89.025 | Sft
18 | Providing & laying of roof insulation comprising of single layer of Tile (9" x 4-1/4" x 1-1/2") grouted with cement sand morter 1:3 laid over 2" thich earth including mud plaster over polythine sheet of 500 gauge. | 62.22 | Sft
19 | 1/2" (20 mm) thick cement plaster 1:4 on walls & columns, etc and curing, etc., complete. | 385.2014 | Sft
20 | 1/2" (20mm) thick cement plaster 1:4 for edges of doors,windows,and ventilators | 126.8988 | Sft
21 | Providing and fixing ceramics tiles for wash basins with 1:2 cement mortar, cutting and finish of tiles | 313.8306 | Sft
22 | Pointing flush or recessed in CM 1:4 to old or new brick work built in any mortar | 311.515 | Sft
23 | Providing and fixing steel ventilators using 1''x1'' angle iron frame, with 2/16'' Ф steel rods, two coats of synthetic enamel paint in adition to one coat of primer/rust proof paint and galvanised wire gauze, 22 guage and 144 mesh to a square inch. | 4.5 | Sft
24 | Providing and fixing steel doors of M.S sheet 18 SWG including all necessary steel fittings, hold fasts and two coats of synthetic enamel paint in addition to one coat of primer/rust proof paint including bolts hinges etc and frame of 1.5" x1.5" x 1/16'' (1.5875 mm) angle iron frame | 33 | Sft
25 | Providing and applying Vinyl emulsion Dulux or berger paint, 2 coats including preparation of surface | 752 | Sft
26 | Providing and applying weather sheild paint on exterior surface of building, including surface preparation and applying two coats | 623.03 | Sft
27 | Providing and fixing 200 gallon water tank (Dura/supper Tuff or equal quality) dubble ply with all necessary fittings, valves,handles etc | 1 | Each
28 | Providing and fixing 1/2'' Ф bib cock (water taps) master, Adam, Sartaj for toilets & hand washing points | 6 | Each
29 | Providing and fixing 4'' Ф strainers for wash basins exit point (Master/Honey master/Adam/sartaj or equivalent quality) | 4 | nos
30 | Providing and fixing 4'' Ф plastic floor waste (Jalli) under vent pipes of wash basins. | 4 | Each
31 | Providing and fixing 3'' Ф PVC pipe (Popular/Royal/equavelant quality) as drain of wash basin (25-30 feet), fixing under ground at least 6'' deep in ground, 3'' PCC (1:2:4) mix over pipe as cover, | 1 | Job
32 | Providing and fitting PPRC (Plasco/Turk Plast or equivalent) (19 mm) Ф pipe for water supply to toilet and hand washing facility connecting with water tank in all respect. | 39 | Each
33 | Providing and fitting Indian water closet (WC) Medium size, (Master/Polo/3 star) with 3'' Ф P-Trap, alongwith fixing/connecting J pipe under walls, Tee/stop cock (steel with brass spendles Master/Sartaj), flexible connecting pipe with flush tanks | 3 | Each
34 | Providing and fitting flush tank of (Master/Adam), or equavelent with all fittings in all respect | 3 | nos
35 | Specials (socket, El-bow,Tee, reducers, point socket & tee,elbow, etc) of PPRC (Plasco/Turk Plast) of 19 mm and for fitting | 1 | Job
36 | Providing and fitting spouts (PVC 3'' Ø) | 2 | nos
37 | Providing and fitting 2'' Ø UPVC pipes as vent pipe of toilet with fly screening head/cap | 2 | nos
38 | Providing and fixing 2'' thick PCC tuff tiles on Ramp surface (10''x10'' or 8''x8'') | 274.65 | nos
39 | Providing and fixing 1'' Ø M/S pipe as Grab rail 5mm holding strips including fine finishing and coloring, fix in walls with 5/8'' bolts drilling in walls, fix bolts with plastic holders | 10 | Rft
40 | Providing and fixing 2'x1.5' steel plaque with embossed write up on toilet block (steel Plate with embossed writing) | 1 | Job
| Sub Total | Total
Amount in words ______________________________________________________________________________
Contractor's Signature & Seal ___________________________________ |  |  |  | Date _____________________

## Measurements
Housing Urban Development & Public Health Engineering Department Division Faisalabad
Detailed Estimate for Child & PWD Friendly School Toilet
Construction of Child & PWD friendly School Toilet (4'x6') & (6'x6') at Government Girl's High school- 96-RB UC # 24 District Faisalabad
MEASUREMENTS
Sr. No. | Descrioption |  | CFT Measurements |  |  |  |  | SFT Measurements
|  |  | Nos. | Length (FT) | Width (FT) D2 | Depth (FT) H | Volume (CFT) (DxExFxG) | Nos. | Length (FT) | Width (FT) | Area (SFT) (I*J*K=L)
1 | Excavation for foundation, underground tanks (rectangular or square), trenches and drains in all kinds of soil including rock and removing all vegetation alongwith their roots and back filling selected excavated material in foundation, plinth or under floor
| Long walls |  | 2 | 13.125 | 2 | 1.25 | 65.625
| Short walls |  | 2 | 8.75 | 2 | 1.25 | 43.75
| Short wall (centeral wall) |  | 1 | 4.75 | 1 | 0.25 | 1.1875
| Retaining wall for plinth protection |  | 1 | 12.5 | 1 | 0.25 | 3.125
| Retaining wall for plinth protection |  | 1 | 18.53 | 1 | 0.25 | 4.6325
| Retaining wall for Ramp (for PWDs) |  | 1 | 0.5 | 19 | 0.66667 | 6.3333
| Drain pipe for hand washing facility |  | 1 | 25 | 1 | 1 | 25
| Total Qauntity:- | [5 empty] | 149.6533
2 | Providing & laying 1:3:6 (1 cement 3 sand and 6 coarse aggregate) cement concrete using graded crush ¾ inch (20mm) and down gauge in foundation including levelling, compacting and curing, etc., complete.
| Long walls |  | 2 | 13.125 | 2 | 0.25 | 13.125
| Short walls |  | 2 | 8.75 | 2 | 0.25 | 8.75
| Short wall (centeral wall) |  | 1 | 4.75 | 1 | 0.25 | 1.1875
| Retaining wall for plinth protection |  | 1 | 12.5 | 1 | 0.25 | 3.125
| Retaining wall for plinth protection |  | 1 | 18.53 | 1 | 0.25 | 4.6325
| Ramp (1/2 basexhieghtxdepth) |  | 1 | 11.115 |  | 5 | 55.575
| Under PVC drain pipe (3''dia) |  | 1 | 25 | 0.75 | 0.25 | 6.25
| Total Qauntity:- | [5 empty] | 92.645
3 | Providing & laying 1:2:4 (1 cement 2 sand and 4 coarse aggregate) cement concrete using graded crush ¾ inch (20mm) and down gauge in foundation including levelling, compacting and curing, etc., complete.
| Sides of drain pipe (3'' PVC) |  | 2 | 25 | 0.125 | 0.125 | 6.25
| Top of drain pipe (3'' PVC) |  | 1 | 25 | 0.75 | 0.25 | 6.25
| Total Qauntity:- | [5 empty] | 12.5
4 | Providing and laying first class solid burnt brick masonry set in cement mortar 1:4 in straight or curved walls 4-1/2" inches (114mm) and less in thickness including scaffolding, raking, out joints and curing, etc., complete in all floors.
1st Step
| Long walls |  | 2 | 12.625 | 1.5 | 0.25 | 9.4688
| Short walls |  | 2 | 9.25 | 1.5 | 0.25 | 6.9375
| Short wall (centeral wall) |  | 1 | 5 | 0.75 | 1 | 3.75
| Retaining wall for plinth protection |  | 1 | 12.5 | 0.75 | 1 | 9.375
| Retaining wall for plinth protection |  | 1 | 18.53 | 0.75 | 1 | 13.8975
2nd Step
| Long walls |  | 2 | 12.4375 | 1.125 | 1.75 | 48.9727
| Short walls |  | 2 | 9.4375 | 1.125 | 1.75 | 37.1602
| Sub Total | [5 empty] | 129.5616
| Wastage 10% | [5 empty] | 12.9562
| Total Qauntity of bricks in plinth area | [5 empty] | 142.5177 |  | Or | Nos | 1995.2481
5 | Providing and laying first class solid burnt brick masonry set in cement mortar 1:5 in straight or curved walls 9" to 13-1/2 inches (228mm to 343mm) thick including scaffolding, raking out joints and curing, etc., complete in foundation, basement and plinth, & super structure all floors, including, all lead and lift.
Supper Structure
| Long walls |  | 2 | 11.87 | 0.75 | 8 | 142.44
| Short walls |  | 2 | 7.5 | 0.75 | 8 | 90
| Short wall (centeral wall) |  | 1 | 7.5 | 0.37 | 8 | 22.2
| Retaining walls of Ramp |  | 2 | 19 | 1.42 | 0.75 | 40.47
| Walls for hand washing facility |  | 4 | 20 | 1.455 | 0.37 | 43.068
| Parapet walls | Long wall (L/W) | 2 | 11.37 | 0.75 | 0.5 | 8.5275
|  | Short wall (S/W) | 2 | 7.5 | 0.75 | 0.5 | 5.625
| Side wall of Hand washing facility (for special children) |  | 1 | 1.6667 | 3.3333 | 0.37 | 2.0556
| Side wall of Hand washing facility (Other side) |  | 1 | 1.6667 | 1.6667 | 0.37 | 1.0278
| Wash basin Wall No-2 |  | 1 | 1.6667 | 2.5 | 0.37 | 1.5417
| Wash basin Wall No-3 |  | 1 | 1.6667 | 2.0833 | 0.37 | 1.2847
| Wash basin Wall No-4 |  | 1 | 1.6667 | 1.6667 | 0.37 | 1.0278
| Edging for wash basins (front) |  | 1 | 7.5 | 0.37 | 0.25 | 0.69375
| Edging for wash basins (Centeral walls) |  | 5 | 1.6667 | 0.37 | 0.25 | 0.77083
| Brick chambers under wash basins (long & short walls) |  | 4 | 1 | 1 | 1 | 4
Deduction
| Door-1 |  | 1 | 3 | 6 | 0.75 | -13.5
| Door-2 |  | 1 | 2.5 | 6 | 0.75 | -11.25
| Vintilators |  | 2 | 1.5 | 1 | 0.75 | -2.25
| Sub Total | [5 empty] | 337.7326
| Wastage 10% | [5 empty] | 33.7733
| Total Qauntity of bricks in plinth area | [5 empty] | 371.5058 |  | Or | Nos | 5201.0818
6 | Providing and laying DPC of 2 inch thick machine mixed 1:2:4 cement concrete using graded crushed boulders 3/4 inch (19 mm) and down gauge including form work, consolidation, finishing, curing etc., complete (a) with one coat of bitumen and one coat of polythene sheet 500 gauge :-
| Long walls |  | 2 | 11.87 | 0.75 | 0.16667 | 2.9675 | 2 | 11.87 | 0.75 | 17.805
| Short walls |  | 2 | 7.5 | 0.75 | 0.16667 | 1.875 | 2 | 7.5 | 0.75 | 11.25
| Short wall (centeral wall) |  | 1 | 7.5 | 0.37 | 0.16667 | 0.4625 | 1 | 7.5 | 0.37 | 2.775
| Total Qauntity:- |  |  |  | Cft |  | 5.305 |  |  | Sft | 31.83
7 | Providing and laying machine mixed reinforced cement concrete using graded crushed boulders 3/4 inch (19mm) and down gauge having a minimum works cube crushing strength of 3000 lbs.per sq. inch(20 N/mm2) at 28 days with a mix not leaner than 1:2:4 including form work and its removal, compacting and curing, etc., but excluding the cost of reinforcement in all floors including all lead and lift.
| Door-No-1 Lentel |  | 1 | 4 | 0.75 | 0.75 | 2.25
| Door-No-2 Lentel |  | 1 | 3.5 | 0.75 | 0.75 | 1.9688
| Ventilators Lentel |  | 2 | 2.5 | 0.75 | 0.75 | 2.8125
| Slabs for hand washing facility |  | 1 | 7.5 | 1.6667 | 0.17 | 2.125
| Total Qauntity:- | [5 empty] | 9.1562
8 | Providing & laying mild steel reinforcement bars with minimum yield stress of 40,000 Psi with and including the cost of straightening, cutting, bending, binding, wastage, and such overlaps as are not shown over the drawings, placing in position on cement concrete 1:2:4 precast or M.S. chairs, tying with binding wire, cost of chair and wires, etc., in all kinds of RCC work in foundation, basement, plinth, ground, and all floors of building including septic tank, underground tank and in projections for future extension.
| Select 3/8'' Ø bars for main and distribution strips for strips should be 9'' apart with 1/2'' cover |  | No of bars | Length (FT) | Hook (12d) | Over Lap (30d) | Total length of one bar | Total Quanitity (Rft) |  | Kg
| Door-No-1 Lentel | Main bar (3/8 '' Ø bars for main ) | 2 | 3.83 | 0 | 0 | 3.83 | 7.66 |  | 1.3064
|  | Strips/distribution bars of 3/8 '' Ø 9'' spacing | 5 | 0.66667 |  |  | 0.66667 | 3.3333 |  | 0.56851
| Door-No-2 Lentel | Main bar (3/8 '' Ø bars for main ) | 2 | 3.33 | 0 | 0 | 3.33 | 6.66 |  | 1.1359
|  | Strips/distribution bars of 3/8 '' Ø 9'' spacing | 5 | 0.66667 |  |  | 0.66667 | 3.3333 |  | 0.56851
| Ventilators Lentel | Main bar (3/8 '' Ø bars for main ) | 2 | 2.33 | 0 | 0 | 2.33 | 4.66 |  | 0.79477
|  | Strips/distribution bars of 3/8 '' Ø 9'' spacing | 4 | 0.66667 |  |  | 0.66667 | 2.6667 |  | 0.45481
| Slabs for hand washing facility | Main bar (3/8 '' Ø bars for main ) | 3 | 7.5 | 0 | 0 | 7.5 | 22.5 |  | 3.8374
|  | Strips/distribution bars of 3/8 '' Ø 9'' spacing | 15 | 1.6667 |  |  | 1.6667 | 25 |  | 4.2638
| Total Qauntity:- | [6 empty] | 28.3133 |  | 12.9302
9 | Providing and fixing 1'' thick Precaste RCC Plates for roof (having 1 bar of 2.54 mm (1 soot) MS steel around collor, with enforcing with one extra bar on sides, and two bars across center of plate horizetal and one vertical for (1.5'x4.5') plates (for 4'x5' toilet room) | [8 empty] | Nos | 4
10 | Providing and fixing 1'' thick Precaste RCC Plates for roof (having 1 bar of 5 mm (2 soot) MS steel around collor, with enforcing with one extra bar on sides, and three bars across center of plate horizetal and one vertical for (1.5'x6.5') plates (for 4'x6 toilet room) | [8 empty] | Nos | 4
11 | Providing and laying 1.5 inch (40mm) thick machine mixed PCC in 1:2:4 cement concrete using graded crushed boulders 1/4 inch (6 mm) and down gauge over roof, finishing, curing etc complete in all respect (for 6'x4' toilet room)
| Roof of both rooms |  | 1 | 11.87 | 7.5 | 0.125 | 11.1281
| Total Qauntity:- | [5 empty] | 11.1281
12 | Providing and laying coping of 1.5 inch (40mm) thick machine mixed 1:2:4 cement concrete using graded crushed boulders 3/4 inch (19mm) and down gauge in ground floor laid in panels including form work, consolidation, finishing, curing etc., complete
| Long walls |  | 2 | 11.87 | 0.37 | 0.125 | 1.098 | 2 | 11.87 | 0.37 | 8.7838
| Long walls |  | 3 | 7.5 | 0.37 | 0.125 | 1.0406 | 3 | 7.5 | 0.37 | 8.325
| Total Qauntity:- (in Cft) |  |  |  |  | Cft | 2.1386 |  |  | Sft | 17.1088
13 | Dry rammed Brick/Stone blast Under Floor mix with25%sand
| Toilet No-1 (4'x6') |  | 1 | 4 | 6 | 0.25 | 6
| Toilet No-2 (6'x6') |  | 1 | 6 | 6 | 0.25 | 9
| Plinth protection (front) |  | 1 | 18.53 | 5 | 0.25 | 23.1625
| Plinth protection (Side) |  | 1 | 12.5 | 5 | 0.25 | 15.625
| Ramp (1/2 basexhieghtxdepth) |  | 1 | 9.5 | 1.25 | 5 | 59.375
| Total Qauntity:- | [5 empty] | 113.1625
14 | Earth filling under floor
| Toilet No-1 (4'x6') |  | 1 | 4 | 6 | 0.75 | 18
| Toilet No-2 (6'x6') |  | 1 | 6 | 6 | 0.75 | 27
| Plinth protection (front) |  | 1 | 18.53 | 5 | 0.75 | 69.4875
| Plinth protection (Side) |  | 1 | 12.5 | 5 | 0.75 | 46.875
| Ramp |  | 1 | 19 | 5 | 0.625 | 59.375
| Total Qauntity:- | [5 empty] | 220.7375
| Earth filling with surplus earth from foundation | [5 empty] | 149.6533
|  | Qty2/3 Of Item No.1 |  |  |  |  | 112.24
| Total Qauntity:- (net required earth) | [5 empty] | 108.4975
15 | Providing and laying floor of 2 inch thick machine mixed 1:2:4 cement concrete using graded crushed boulders 3/4 inch (19 mm) and down gauge in ground floor laid in panels with marble dividers of 1/2"x2", consolidation, finishing, curing etc., complete
| Toilet No-1 (4'x6') | [6 empty] | 1 | 4 | 6 | 24
| Toilet No-2 (6'x6') | [6 empty] | 1 | 6 | 6 | 36
| Plinth protection (front) | [6 empty] | 1 | 18.53 | 5 | 92.65
| Plinth protection (Side) | [6 empty] | 1 | 12.5 | 5 | 62.5
| Ramp | [6 empty] | 1 | 19 | 5 | 95
| Total Qauntity:- | [6 empty] | CFT | 49.624 | Sft | 310.15
16 | Providing and laying 1.5'' (38 mm) thick layer of earth over roofs
| Toilet No-1 (4'x6') |  | 1 | 4 | 6 | 0.125 | 3
| Toilet No-2 (6'x6') |  | 1 | 6 | 6 | 0.125 | 4.5
| Total Qauntity:- (CFT) | [5 empty] | 7.5
17 | Providing and laying of 1/2'' (20 mm) thick mud plaster over roofs with bhusa (chuff not large 2 cm) @ 1kg / cft of earth
| Roof of Toilet No-1 & 2 (11.87'x7.5') | [6 empty] | 1 | 11.87 | 7.5 | 89.025
| Total Qauntity:- | [5 empty] | 0 | Cft |  | Sft | 89.025
18 | Providing & laying of roof insulation comprising of single layer of Tile (9" x 4-1/4" x 1-1/2") grouted with cement sand morter 1:3 laid over 2" thich earth including mud plaster over polythine sheet of 500 gauge.
| Roof of both Toilet rooms | [6 empty] | 1 | 10.37 | 6 | 62.22
| Total Qauntity:- | [8 empty] | Sft | 62.22
19 | 1/2" (20 mm) thick cement plaster 1:4 on walls & columns, etc and curing, etc., complete.
| Toilet No-1 (4'x6') | Long walls (inner) | [5 empty] | 2 | 6 | 8 | 96
|  | Short walls (inner) | [5 empty] | 2 | 4 | 8 | 64
| Toilet No-2 (6'x6') | Long walls (inner) | [5 empty] | 2 | 6 | 8 | 96
|  | Short walls (inner) | [5 empty] | 2 | 6 | 8 | 96
| Parapet wall | Long walls with coping | [5 empty] | 2 | 11.87 | 0.66667 | 15.8267
|  | Short walls with coping | [5 empty] | 2 | 7.5 | 0.66667 | 10
|  | Top (L/W) | [5 empty] | 2 | 11.87 | 0.375 | 8.9025
|  | Top (S/W) | [5 empty] | 2 | 7.5 | 0.375 | 5.625
| Lentles | Door-No-1 | [5 empty] | 1 | 3.5 | 0.25 | 0.875
|  | Door-No-2 | [5 empty] | 1 | 3 | 0.25 | 0.75
| vintilators | [6 empty] | 2 | 2 | 0.25 | 1
| Drain chambers | inner | [5 empty] | 16 | 0.75 | 0.75 | 9
|  | Top | [5 empty] | 16 | 0.25 | 0.25 | 1
| Wash basins (inner) | 1st basin (PWD) sides (L/W) | [5 empty] | 2 | 1.8333 | 0.25 | 0.91667
|  | 1st basin (PWD) sides (S/W) | [5 empty] | 2 | 1.25 | 0.25 | 0.625
|  | Floor | [5 empty] | 1 | 1.8333 | 1.25 | 2.2917
|  | 2nd basin sides (L/W) | [5 empty] | 2 | 1.1667 | 0.25 | 0.58333
|  | 2nd basin sides (S/W) | [5 empty] | 2 | 1.25 | 0.25 | 0.625
|  | Floor | [5 empty] | 1 | 1.1667 | 1.25 | 1.4583
|  | 3rd & 4th basins sides (L/W) | [5 empty] | 4 | 1.25 | 0.25 | 1.25
|  | 3rd & 4th basins sides (S/W) | [5 empty] | 4 | 1.25 | 0.25 | 1.25
|  | Floor | [5 empty] | 2 | 1.25 | 1.25 | 3.125
| Wash basins (Outer) | Long front | [5 empty] | 1 | 7.5 | 0.25 | 1.875
|  | Sides | [5 empty] | 5 | 1.6667 | 0.25 | 2.0833
|  | Edges (1st) PWD | [5 empty] | 1 | 1.6667 | 0.25 | 0.41667
|  | Edges (2nd) | [5 empty] | 1 | 1.6667 | 0.41667 | 0.69444
|  | Edges (3rd) | [5 empty] | 1 | 1.6667 | 0.41667 | 0.69444
|  | Side wall of 4th basin | [5 empty] | 1 | 1.6667 | 1.25 | 2.0833
Deductions
| door-1 | [6 empty] | 1 | 3 | 6 | -18
| door-2 | [6 empty] | 1 | 2.5 | 6 | -15
| vintilators | [6 empty] | 2 | 1.5 | 1 | -3
| Openings of hand washing facility for drain pipes | 1st opening | [5 empty] | 1 | 0.75 | 1.25 | -0.9375
|  | 2nd opening | [5 empty] | 1 | 0.75 | 1.6667 | -1.25
|  | 3rd opening | [5 empty] | 1 | 0.75 | 2.0833 | -1.5625
| Total Qauntity:- | [9 empty] | 385.2014
20 | 1/2" (20mm) thick cement plaster 1:4 for edges of doors,windows,and ventilators
| Door-1 | Sides | [5 empty] | 2 | 6 | 0.37 | 4.44
|  | Top | [5 empty] | 1 | 3 | 0.75 | 2.25
| Door-2 | Sides | [5 empty] | 2 | 6 | 0.37 | 4.44
|  | Top & bottom | [5 empty] | 1 | 2.5 | 0.37 | 0.925
| Ventilators | Top & bottom | [5 empty] | 4 | 1.5 | 0.75 | 4.5
|  | Sides | [5 empty] | 4 | 1 | 0.75 | 3
| Hand washing Facility walls | Part-1 | [5 empty] | 1 | 53 | 1.25 | 66.25
|  | Part-2 | [5 empty] | 1 | 18 | 0.16667 | 3
|  | Part-3 | [5 empty] | 1 | 17 | 0.83333 | 14.1667
|  | Part-4 (part of 2nd wall of PWD basin) | [5 empty] | 1 | 0.375 | 0.25 | 0.09375
|  | Part-5 (side) PWD basin | [5 empty] | 1 | 1.6667 | 2.3333 | 3.8889
|  | Part-5 (front) PWD basin | [5 empty] | 1 | 0.75 | 2.3333 | 1.75
|  | Part-5 (inner) PWD basin | [5 empty] | 2 | 1.6667 | 2.3333 | 7.7778
| Inner of openings | 1st opening | [5 empty] | 2 | 1.6667 | 1.25 | 4.1667
|  | 2nd opening | [5 empty] | 1 | 1.6667 | 1.6667 | 2.7778
|  | 3rd opening | [5 empty] | 1 | 1.6667 | 2.0833 | 3.4722
| Total Qauntity:- | [9 empty] | 126.8988
21 | Providing and fixing ceramics tiles for wash basins with 1:2 cement mortar, cutting and finish of tiles
| Top Front of hand wash facility | [6 empty] | 1 | 7.5 | 0.25 | 1.875
| Top Sides | [6 empty] | 5 | 1.6667 | 0.25 | 2.0833
| Inner of basins | (PWD basin) L/W | [5 empty] | 2 | 1.8333 | 0.25 | 0.91667
|  | Bottom | [5 empty] | 1 | 1.8333 | 1.25 | 2.2917
|  | 2nd basin (L/W) | [5 empty] | 2 | 1.1667 | 0.25 | 0.58333
|  | Bottom | [5 empty] | 1 | 1.1667 | 1.25 | 1.4583
|  | 3rd & 4th basins (L/W) | [5 empty] | 4 | 1.25 | 0.25 | 1.25
|  | Short walls of all basins | [5 empty] | 8 | 1.25 | 0.25 | 2.5
|  | Skerting On basin's wall | [5 empty] | 1 | 7.5 | 1 | 7.5
|  | Side wall of hand washing facility (front) | [5 empty] | 1 | 1.6667 | 2.3333 | 3.8889
|  | Side wall of hand washing facility (Rear) | [5 empty] | 1 | 1.6667 | 1.25 | 2.0833
Inside the toilets
| Toilet (4'x6') | Long wall | [5 empty] | 2 | 6 | 5 | 60
|  | Short | [5 empty] | 2 | 4 | 5 | 40
| Door sides (both rooms) | Door sides | [5 empty] | 4 | 0.37 | 5 | 7.4
| Toilet (6'x6') | Long wall | [5 empty] | 2 | 6 | 5 | 60
|  | Short | [5 empty] | 2 | 6 | 5 | 60
| Floor (4'x6') | [6 empty] | 1 | 4 | 6 | 24
| Floor (6'x6') | [6 empty] | 1 | 6 | 6 | 36
| Total Qauntity:- | [8 empty] | Sft | 313.8306
22 | Pointing flush or recessed in CM 1:4 to old or new brick work built in any mortar
Below DPC
|  | L/W | [5 empty] | 2 | 12.24 | 1 | 24.48
|  | S/W | [5 empty] | 2 | 7.87 | 1 | 15.74
| Above DPC | L/W | [5 empty] | 2 | 11.87 | 8 | 189.92
|  | S/W | [5 empty] | 2 | 7.5 | 8 | 120
Deductions
| Door-1 (opening) | [6 empty] | 1 | 3 | 6 | -18
| Door-2 (opening) | [6 empty] | 1 | 2.5 | 6 | -15
| Ventilator (opening) | [6 empty] | 2 | 1.5 | 1 | -3
| Door Lentles | Door-No-1 (3'x6') | [5 empty] | 1 | 3.5 | 0.25 | -0.875
|  | Door-No-2 (2.5'x6') | [5 empty] | 1 | 3 | 0.25 | -0.75
|  | Ventilators (1.5'x1') | [5 empty] | 2 | 2 | 0.25 | -1
| Total Qauntity:- | [9 empty] | 311.515
23 | Providing and fixing steel ventilators using 1''x1'' angle iron frame, with 2/16'' Ф steel rods, two coats of synthetic enamel paint in adition to one coat of primer/rust proof paint and galvanised wire gauze, 22 guage and 144 mesh to a square inch.
| Ventilators (1.5'x1.5') | [6 empty] | 2 | 1.5 | 1.5 | 4.5
| Total Quantity:- | [9 empty] | 4.5
24 | Providing and fixing steel doors of M.S sheet 18 SWG including all necessary steel fittings, hold fasts and two coats of synthetic enamel paint in addition to one coat of primer/rust proof paint including bolts hinges etc and frame of 1.5" x1.5" x 1/16'' (1.5875 mm) angle iron frame
| Door (3'x6') | [6 empty] | 1 | 3 | 6 | 18
| Door (2.5'x6') | [6 empty] | 1 | 2.5 | 6 | 15
| Total Quantity:- | [9 empty] | 33
25 | Providing and applying Vinyl emulsion Dulux or berger paint, 2 coats including preparation of surface
| Toilet No-1 (4'x6') | Long walls | [5 empty] | 2 | 6 | 8 | 96
|  | Short walls | [5 empty] | 2 | 4 | 8 | 64
| Toilet No-2 (6'x6') | Long walls | [5 empty] | 2 | 6 | 8 | 96
|  | Short walls | [5 empty] | 2 | 6 | 8 | 96
| Roof Toilet No-1 (4'x6') | [6 empty] | 1 | 4 | 6 | 24
| Roof Toilet No-1 (6''x6') | [6 empty] | 1 | 6 | 6 | 36
Deductions
| Door-1 | [6 empty] | 1 | 3 | 6 | -18
| Door-2 | [6 empty] | 1 | 2.5 | 6 | -15
| Ventilator | [6 empty] | 2 | 1.5 | 1 | -3
| Sub Total | [9 empty] | 376
| Total Quantity:- (2 coats) | [8 empty] | Sft | 752
26 | Providing and applying weather sheild paint on exterior surface of building, including surface preparation and applying two coats
| Quantity as per item No-14 (pointing) | [9 empty] | 311.515
| Sub Total | [9 empty] | 311.515
| Total Quantity:- (2 coats) | [9 empty] | 623.03
27 | Providing and fixing 200 gallon water tank (Dura/supper Tuff or equal quality) dubble ply with all necessary fittings, valves,handles etc | [8 empty] | No | 1
28 | Providing and fixing 1/2'' Ф bib cock (water taps) master, Adam, Sartaj for toilets & hand washing points | [8 empty] | No | 6
29 | Providing and fixing 4'' Ф strainers for wash basins exit point (Master/Honey master/Adam/sartaj or equivalent quality) | [8 empty] | No | 4
30 | Providing and fixing 4'' Ф plastic floor waste (Jalli) under vent pipes of wash basins. | [8 empty] | No | 4
31 | Providing and fixing 3'' Ф PVC pipe (Popular/Royal/equavelant quality) as drain of wash basin (25-30 feet), fixing under ground at least 6'' deep in ground, 3'' PCC (1:2:4) mix over pipe as cover, | [8 empty] | Job | 1
32 | Providing and fitting PPRC (Plasco/Turk Plast or equivalent) (19 mm) Ф pipe for water supply to toilet and hand washing facility connecting with water tank in all respect. | [8 empty] | Rft | 39
33 | Providing and fitting Indian water closet (WC) Medium size, (Master/Polo/3 star) with 3'' Ф P-Trap, alongwith fixing/connecting J pipe under walls, Tee/stop cock (steel with brass spendles Master/Sartaj), flexible connecting pipe with flush tanks | [8 empty] | No | 3
34 | Providing and fitting flush tank of (Master/Adam), or equavelent with all fittings in all respect | [8 empty] | No | 3
35 | Specials (socket, El-bow,Tee, reducers, point socket & tee,elbow, etc) of PPRC (Plasco/Turk Plast) of 19 mm and for fitting | [8 empty] | Job | 1
36 | Providing and fitting spouts (PVC 3'' Ø) | [8 empty] | No | 2
37 | Providing and fitting 2'' Ø UPVC pipes as vent pipe of toilet with fly screening head/cap | [8 empty] | No | 2
38 | Providing and fixing 2'' thick PCC tuff tiles on Ramp surface (10''x10'' or 8''x8'') | [6 empty] | Sft | 91.55 | No | 274.65
39 | Providing and fixing 1'' Ø M/S pipe as Grab rail 5mm holding strips including fine finishing and coloring, fix in walls with 5/8'' bolts drilling in walls, fix bolts with plastic holders | [8 empty] | Rft | 10
40 | Providing and fixing 2'x1.5' steel plaque with embossed write up on toilet block (steel Plate with embossed writing) | [8 empty] | Job | 1

## Plan
Housing Urban Development & Public Health Engineering Department Division Faisalabad
Construction of Child & PWD friendly School Toilet (4'x6') & (6'x6') at Government Girl's High school- 96-RB UC # 24 District Faisalabad
9'' |  |  | 4' |  |  | 9'' |  | 4' |  |  | 9'' | 1.5'
9''
|  |  |  | 9'' |  |  | 9'' | [9 empty] | LEGEND
18''x20''
[17 empty] | Description | Size | Qty
[5 empty] | 9'' |  | 9'' | [9 empty] | D -1 | 2.5'x 6' | 1
[17 empty] | D -2 | 3'x 6' | 1
[17 empty] | V | 1.5'x1.5' | 2
6'
| Toilet 4'x6'x8' | [5 empty] | Toilet 6'x6'x8'
5'
|  | D-1 | [7 empty] | D-2 |  |  |  |  | 9''
[8 empty] | 5' |  |  |  | 20''
Ramp with a slop of 1:16
[8 empty] | 18'-8'' | 5'
18'-8''
1'-2''
18'-7.5''
D=4.92'
15''x15''
22''x15''
14''x15''
15''x15''
Septic Tank 9'x4'x4'

## X-Sec of Toilet
Housing Urban Development & Public Health Engineering Department Division Faisalabad
Construction of Child & PWD friendly School Toilet (4'x6') & (6'x6') at Government Girl's High school- 96-RB UC # 24 District Faisalabad
[6 empty] | 4.5'' | [18 empty] | 4.5''
|  |  |  | 1.5'' | [5 empty] | Laying of tiles (9''x4 1/2''x1.5'') over mud plaster with cement grouting in 1:3 | [16 empty] | 1.5'' thick coping in 1:2:4
6''
Brick tiles with 1:3 grouting
1.5'' mud plaster over roof
1.5'' thick layer of earth on roof
1.5'' thick layer of PCC in 1:2:4 overPlates
8'
1'' thick earth filling on roof slab
Precaste RCC roof plates
[6 empty] | 9'' |  |  |  |  | 11/2'' thick mud plaster with chuff (bhusa) |  |  |  | 4.5'' | [8 empty] | 9''
[7 empty] | 4' | [8 empty] | 6'
1.5'' thick PCC (1:2:4) in floor
[5 empty] | 2.25'' |  | 2.25'' | [11 empty] | 11.87 |  |  |  | 2.25''
2'' thick DPC in 1:2:4
3'' thick Brick Ballast dray |  | 1'
9''
13.5'
Ground Level | [16 empty] | 3'' | [10 empty] | 9'' | 2.5' | 3''
13.5''
1'
|  |  |  | 2.25'' |  |  |  | 2.25'' | [13 empty] | 2.25'' |  |  |  | 2.25''
3''
|  |  |  | 18'' | [19 empty] | 18''
|  |  | 3'' | [5 empty] | 3'' | [11 empty] | 3'' | [5 empty] | 3''
| 3'' | [18 empty] | 3'' | [7 empty] | 3''
|  |  | PCC 1:3:6 | [17 empty] | PCC 1:3:6
|  |  | 24'' | [17 empty] | 24''

## hand washing point
Housing Urban Development & Public Health Engineering Department Division Faisalabad
Construction of Child & PWD friendly School Toilet (4'x6') & (6'x6') at Government Girl's High school- 96-RB UC # 24 District Faisalabad
20''
|  |  | 22'' |  | 15''
[7 empty] | 15'' |  | 14''
3/4'' PVC pipe to be fixed in RCC slab
| 3'' |  | RCC Slab
1'x1'x1' brick masonary with 2'' thick PCC cover
|  |  |  | 22'' |  | 15'' |  | 15'' |  | 14''

## Sheet1
Housing Urban Development & Public Health Engineering Department Division Faisalabad
Construction of Child & PWD friendly School Toilet (4'x6') & (6'x6') at Government Girl's High school- 96-RB UC # 24 District Faisalabad
Design and specifiactions for toilet Grab Rails
1'' Ф M/S pipe with fine finishing and color
use 5/8'' Ф bolts fix in walls with drilling & holders
4'-6''
9''
2'
|  |  | 22'' | 22'' |  | 2'
18''
15''