## Tender
Housing Urban Development & Public Health Engineering Department Division Faisalabad
Construction of Septic Tank at Government Boy's Elementary School 99-RB UC # 24 District Faisalabad
ABSTRACT OF COST
Quantity/cost
Sr. | Description of work | Quantity | Unit | Rate | Amount
1 | Excavation for foundation, underground tanks (rectangular or square), trenches and drains in all kinds of soil including rock and removing all vegetation alongwith their roots and back filling selected excavated material in foundation, plinth or under floor | 312 | Cft
2 | Providing & laying 1:3:6 (1 cement 3 sand and 6 coarse aggregate) cement concrete using graded crush ¾ inch (20mm) and down gauge in foundation including levelling, compacting and curing, etc., complete. | 18 | Cft
3 | Providing and laying first class solid burnt brick masonry set in cement mortar 1:5 in straight or curved walls 9" to 13-1/2 inches (228mm to 343mm) thick including scaffolding, raking out joints and curing, etc., complete in foundation, basement and plinth, & super structure all floors, including, all lead and lift. | 116 | Cft
4 | Providing and laying machine mixed reinforced cement concrete using graded crushed boulders 3/4 inch (19mm) and down gauge having a minimum works cube crushing strength of 3000 lbs.per sq. inch(20 N/mm2) at 28 days with a mix not leaner than 1:2:4 including form work and its removal, compacting and curing, etc., but excluding the cost of reinforcement in all floors including all lead and lift. | 21 | Cft
5 | Providing & laying mild steel reinforcement bars with minimum yield stress of 40,000 Psi with and including the cost of straightening, cutting, bending, binding, wastage, and such overlaps as are not shown over the drawings, placing in position on cement concrete 1:2:4 precast or M.S. chairs, tying with binding wire, cost of chair and wires, etc., in all kinds of RCC work in foundation, basement, plinth, ground, and all floors of building including septic tank, underground tank and in projections for future extension. | 30 | kg
6 | Providing and laying floor of 2 inch thick machine mixed 1:2:4 cement concrete using graded crushed boulders 3/4 inch (19 mm) and down gauge in ground floor laid in panels , consolidation, finishing, curing etc., complete in all respect | 36 | Sft
7 | 1/2" (20 mm) thick cement plaster 1:4 on walls & columns, etc and curing, etc., complete. | 150 | Sft
| Sub Total | Total
Amount in words ______________________________________________________________________________
Contractor's Signature & Seal ___________________________________ |  |  |  | Date _____________________

## Measurements
Housing Urban Development & Public Health Engineering Department Division Faisalabad
Detailed Estimate for Septic Tank (9'x4'x4')
Construction of Septic Tank at Government Boy's Elementary School 99-RB UC # 24 District Faisalabad
MEASUREMENTS
Sr. No. | Descrioption |  | CFT Measurements |  |  |  |  | SFT Measurements
|  |  | Nos. | Length (FT) | Width (FT) D2 | Depth (FT) H | Volume (CFT) (DxExFxG) | Nos. | Length (FT) | Width (FT) | Area (SFT) (I*J*K=L)
1 | Excavation for foundation, underground tanks (rectangular or square), trenches and drains in all kinds of soil including rock and removing all vegetation alongwith their roots and back filling selected excavated material in foundation, plinth or under floor
| Septic Tank |  | 1 | 12 | 6 | 4.5 | 324
| drain pipe |  | 1 | 30 | 1 | 1 | 30
| Total Qauntity:- | [5 empty] | 354
2 | Providing & laying 1:3:6 (1 cement 3 sand and 6 coarse aggregate) cement concrete using graded crush ¾ inch (20mm) and down gauge in foundation including levelling, compacting and curing, etc., complete.
| Septic Tank |  | 1 | 12 | 6 | 0.25 | 18
| Total Qauntity:- | [5 empty] | 18
3 | Providing and laying first class solid burnt brick masonry set in cement mortar 1:5 in straight or curved walls 9" to 13-1/2 inches (228mm to 343mm) thick including scaffolding, raking out joints and curing, etc., complete in foundation, basement and plinth, & super structure all floors, including, all lead and lift.
| Long walls |  | 2 | 11.25 | 0.75 | 4.25 | 71.7188
| short walls |  | 2 | 5.5 | 0.75 | 4.25 | 35.0625
| short walls (internal walls) |  | 2 | 4 | 0.37 | 4.25 | 12.58
| Total Qauntity:- | [5 empty] | 119.3612
4 | Providing and laying machine mixed reinforced cement concrete using graded crushed boulders 3/4 inch (19mm) and down gauge having a minimum works cube crushing strength of 3000 lbs.per sq. inch(20 N/mm2) at 28 days with a mix not leaner than 1:2:4 including form work and its removal, compacting and curing, etc., but excluding the cost of reinforcement in all floors including all lead and lift.
Cover slab of septic tank
|  | Three slabs | 3 | 3.94 | 5.5 | 0.33 | 21.4533
| Total Qauntity:- |  |  |  | Cft |  | 21.4533
5 | Providing & laying mild steel reinforcement bars with minimum yield stress of 40,000 Psi with and including the cost of straightening, cutting, bending, binding, wastage, and such overlaps as are not shown over the drawings, placing in position on cement concrete 1:2:4 precast or M.S. chairs, tying with binding wire, cost of chair and wires, etc., in all kinds of RCC work in foundation, basement, plinth, ground, and all floors of building including septic tank, underground tank and in projections for future extension.
| Cover slab of septic tank Select 3/8'' Ø bars at 7'' C/C for both main and distribution bars |  | No | No of bars | Length | Total length (Rft) | weight of bars (Lbs) | weight of bars (Kg)
| For three slabs | Main Bars | 3 | 9 | 3.86 | 104.22 | 31.9955 | 14.5131
|  | Distribution bars | 3 | 7 | 5.42 | 113.82 | 34.9427 | 15.8499
|  | Total |  |  |  |  | 66.9383 | 30.363
Total Qauntity:- (in Rft)
6 | Providing and laying floor of 2 inch thick machine mixed 1:2:4 cement concrete using graded crushed boulders 3/4 inch (19 mm) and down gauge in ground floor laid in panels , consolidation, finishing, curing etc., complete in all respect
| Septic Tank Chamber | Three no of chambers | [5 empty] | 3 | 4 | 3 | 36
| Total Qauntity:- | [8 empty] | Sft | 36
7 | 1/2" (20 mm) thick cement plaster 1:4 on walls & columns, etc and curing, etc., complete.
| All chambers | Long walls (inner) | [5 empty] | 2 | 9.75 | 4 | 78
|  | Short walls (inner) | [5 empty] | 6 | 4 | 3 | 72
| Total Qauntity:- | [8 empty] | Sft | 150

## Plan
Housing Urban Development & Public Health Engineering Department Division Faisalabad
Construction of Septic Tank at Government Boy's Elementary School 99-RB UC # 24 District Faisalabad
Plan of Septic Tank (11.25'x5.5'x4') outer
D
5'-6'' | [12 empty] | 9''
| B | [14 empty] | A
[5 empty] | 4' |  |  |  | 4' |  |  |  |  | 4'
|  |  | 3' |  |  |  | 3' |  |  |  | 3'
|  | 9'' |  |  |  | 4.5'' |  |  |  | 4.5'' |  |  |  |  | 9''
9''
11'-3''
C
|  |  |  | 3.935 |  |  |  | 3.94 |  |  |  | 3.935
0.185

## X-Sec & Plan of Septic Tank
Housing Urban Development & Public Health Engineering Department Division Faisalabad
Construction of Septic Tank at Government Boy's Elementary School 99-RB UC # 24 District Faisalabad
Plan of Septic Tank 9'x4' x4'
|  |  |  | AB-X-Sec of Septic Tank | [13 empty] | CD-X-Sec of Septic Tank (11.25'x5.5'x4')
Covering slab in 1:2:4
| Outlet | [12 empty] | 3'' |  |  | 3''
[14 empty] | 6'' | In let 4'' Ø PVC pipe |  | 6''
GL
4'' Ø PVC pipe
[10 empty] | 4' | [8 empty] | 4'
[5 empty] | 3' |  |  | 3' |  |  | 3' | [7 empty] | 3'
[9 empty] | 0.37' |  |  |  |  | 3.5' |  |  | 3.5'
|  |  |  | 9'' | [7 empty] | 9''
[6 empty] | 0.37' |  |  | 0.37'
2'' thick PCC 1:2:4
|  |  | 3'' | [9 empty] | 3'' | 2'' | PCC 1:2:4 as floor |  | 2''
[7 empty] | PCC 1:3:6 | [6 empty] | 3'' | PCC 1:3:6 as hard core |  | 3''
11'-9''

## steel febrication
Housing Urban Development & Public Health Engineering Department Division Faisalabad
Steel Febrication for Slab of Septic Tank (5'-5''x 3'-10'')
Construction of Septic Tank at Government Boy's Elementary School 99-RB UC # 24 District Faisalabad
3/8'' Ø bars as Main & distribution bars @ 7'' c/c spacing 1'' cover
9 bars of 3.86' for each slab
7 bars of 5.42' for each slab
3'-11''
spacing of bars 7''C/C
5'-6''