## Tender
Housing Urban Development & Public Health Engineering Department Division Sahiwal
Government Boy's High School 58/JB UC 177 District Faisalabad
Desilting of floors/WC of two toilets, Provision 4 no of flush tanks, 4 no of wash basins, distemper, weather shield, raising of floors (2 toilet rooms),re-fixing of WCs , raising of roof (two toilets) and roof slabs with treatment
ABSTRACT OF QUANTITY & COST
Quantity/cost
Sr. | Description of work | Quantity | Unit | Unit Rate | Amount
1 | Providing & fitting of 4 number of wash basins medium size (master), connecting with existing water supply with stop cocks, single tape (steel) (sartaj/master), connection pipes (steel) strainer (jali) and waste pipe, fixing 10-15 feet pipe 4'' (Popular/Royal or similar quality) to disposing off waste water complete in all respect | 4 | Job
2 | Providing & fitting of flush tanks (master), connecting with existing water supply with stop cocks, (sartaj/master/Adam) connecting with pipe complete in all respect | 4 | Job
3 | Providing and applying Vinyl emulsion Dulux or berger paint, 2 coats including preparation of surface | 596 | Job
4 | Providing and applying weather sheild paint on exterior surface of building, including surface preparation and applying two coats | 491.3889 | Job
5 | Providing and fixing 3'' Ф PVC pipe (Popular/Royal/equavelant quality) as drain of wash basin and septic tank (50 feet), fixing under ground at least 6'' deep in ground, 3'' PCC (1:2:4) mix over pipe as cover, | 1 | sft
6 | Dismeteling of concrete 1:2:4/floor, WC and other accessaries of toilets (floors of toilets), | 40 | Job
7 | Transportation of earth all type when the total distance including the lead cover in the item is more then 1000 ft | 30 | cft
8 | Compaction of earthwork (soft, ordinary & hard soil), compaction by hand rammed in all respect | 30 | cft
9 | Dry rammed brick or stone ballast, 1½" to 2"( 40 mm to 50 mm) gauge. (3'' thick bottom layer ) | 20 | cft
10 | Providing and laying floor of 2 inch thick machine mixed 1:2:4 cement concrete using graded crushed boulders 3/4 inch (19 mm) and down gauge in ground floor laid in panels with marble dividers of 1/2"x2", consolidation, finishing, curing etc., complete | 40 | cft
11 | Providing and fitting indian water closet (WC) large size, Master, pole, 3 star or equavelent with 3'' Ф P-Trap, stop cock, connection pipe, J-pipe (connect with flush tank) complete in all respect | 2 | sft
Sub Total

## Measurements
Housing Urban Development & Public Health Engineering Department Division Faisalabad
Government Boy's High School 58/JB UC 177 District Faisalabad
Desilting of floors/WC of two toilets, Provision 4 no of flush tanks, 4 no of wash basins, distemper, weather shield, raising of floors (2 toilet rooms),re-fixing of WCs , raising of roof (two toilets) and roof slabs with treatment
MEASUREMENTS
Sr. No. | Description |  | CFT Measurements |  |  |  |  | SFT Measurements
|  |  | Nos. | Length (FT) | Width (FT) D2 | Depth (FT) H | Volume (CFT) (DxExFxG) | Nos. | Length (FT) | Width (FT) | Area (SFT) (I*J*K=L)
1 | Providing & fitting of 4 number of wash basins medium size (master), connecting with existing water supply with stop cocks, single tape (steel) (sartaj/master), connection pipes (steel) strainer (jali) and waste pipe, fixing 10-15 feet pipe 4'' (Popular/Royal or similar quality) to disposing off waste water complete in all respect | [9 empty] | 4
| Total Qauntity:- | [8 empty] | Job | 4
2 | Providing & fitting of flush tanks (master), connecting with existing water supply with stop cocks, (sartaj/master/Adam) connecting with pipe complete in all respect | [9 empty] | 4
| Total Qauntity:- | [8 empty] | Job | 4
3 | Providing and applying Vinyl emulsion Dulux or berger paint, 2 coats including preparation of surface
|  | L/W | [5 empty] | 4 | 5 | 9.3333 | 186.6667
|  | S/W | [5 empty] | 4 | 4 | 9.3333 | 149.3333
| Deduction of door | [6 empty] | 2 | 2.5 | 7 | -35
| Ventilators | [6 empty] | 2 | 1.5 | 1 | -3
| Sub Total:- | [8 empty] | Sft | 298
| Total Qauntity:- (2 coats) | [8 empty] | Sft | 596
4 | Providing and applying weather sheild paint on exterior surface of building, including surface preparation and applying two coats
| Below DPC | L/W | [5 empty] | 2 | 10.3333 | 1.5 | 31
|  | S/W | [5 empty] | 1 | 10.3333 | 1.5 | 15.5
| Above DPC | L/W | [5 empty] | 1 | 10.3333 | 11.8333 | 122.2778
|  | S/W | [5 empty] | 1 | 6.5 | 11.8333 | 76.9167
| Deduction of door | [6 empty] | 2 | 2.5 | 7 | -35
| Ventilators | [6 empty] | 2 | 1.5 | 1 | -3
| Sub Total:- | [9 empty] | 245.6944
| Total Qauntity:- (2 coats) | [8 empty] | Sft | 491.3889
5 | Providing and fixing 3'' Ф PVC pipe (Popular/Royal/equavelant quality) as drain of wash basin and septic tank (50 feet), fixing under ground at least 6'' deep in ground, 3'' PCC (1:2:4) mix over pipe as cover, | [8 empty] | Job | 1
6 | Dismeteling of concrete 1:2:4/floor, WC and other accessaries of toilets (floors of toilets),
| Two no of floor (5'x4') |  | 2 | 5 | 4 | 1 | 40
| Total Quantity:- | [5 empty] | 40
7 | Transportation of earth all type when the total distance including the lead cover in the item is more then 1000 ft
| Providing earth for filling under floors of toilets (5'x'4') |  | 2 | 5 | 4 | 0.75 | 30
| Total Qauntity:- | [5 empty] | 30
8 | Compaction of earthwork (soft, ordinary & hard soil), compaction by hand rammed in all respect
| Total Qauntity:- (Qty as per item No-2) | [5 empty] | 30
9 | Dry rammed brick or stone ballast, 1½" to 2"( 40 mm to 50 mm) gauge. (3'' thick bottom layer )
| under floors of toilets |  | 2 | 5 | 4 | 0.5 | 20
| Total Quantity:- (in Cft) |  |  |  |  | Cft | 20
10 | Providing and laying floor of 2 inch thick machine mixed 1:2:4 cement concrete using graded crushed boulders 3/4 inch (19 mm) and down gauge in ground floor laid in panels with marble dividers of 1/2"x2", consolidation, finishing, curing etc., complete
| Toilet (5'x4') | [6 empty] | 2 | 5 | 4 | 40
| Total Quantity:- (in sft) | [8 empty] | Sft | 40
11 | Providing and fitting indian water closet (WC) large size, Master, pole, 3 star or equavelent with 3'' Ф P-Trap, stop cock, connection pipe, J-pipe (connect with flush tank) complete in all respect | [8 empty] | No | 2
12 | Providing and laying first class solid burnt brick masonry set in cement mortar 1:4 in straight or curved walls 4-1/2" inches (114mm) and less in thickness including scaffolding, raking, out joints and curing, etc., complete in all floors.
Toilet (5'x4') walls
|  | L/W | 2 | 10.3333 | 0.75 | 1 | 15.5
|  | S/W | 2 | 5 | 0.75 | 1 | 7.5
|  | S/W (center) | 2 | 5 | 0.37 | 1 | 3.7
| Sub Total | [5 empty] | 26.7
| Wastage 10% | [5 empty] | 2.67
| Total Qauntity of bricks in plinth area | [5 empty] | 29.37 |  | Or | Nos | 411.18
13 | Cement plaster 1:4 upto 20' (6.00 m) height:- b) ½" (13 mm) thick
|  | L/W | [5 empty] | 4 | 10.3333 | 1 | 41.3333
|  | S/W | [5 empty] | 6 | 5 | 1 | 30
| Total Qauntity:- | [8 empty] | Sft | 71.3333
14 | Providing and fixing 1'' thick Precaste RCC Plates for roof (having 1 bar of 2.54 mm (1 soot) MS steel around collor, with enforcing with one extra bar on sides, and two bars across center of plate horizetal and one vertical for (1.5'x4.5') plates | [8 empty] | Nos | 4
15 | Providing and fixing 1'' thick Precaste RCC Plates for roof (having 1 bar of 5 mm (2 soot) MS steel around collor, with enforcing with one extra bar on sides, and three bars across center of plate horizetal and one vertical for (1.5'x6.5') plates | [8 empty] | Nos | 4
16 | Providing and laying 1.5 inch (40mm) thick machine mixed PCC in 1:2:4 cement concrete using graded crushed boulders 1/4 inch (6 mm) and down gauge over roof, finishing, curing etc complete in all respect
| Roof of both rooms |  | 1 | 10.3333 | 6.6667 | 0.125 | 8.6111 | 1 | 10.3333 | 6.6667 | 68.8889
| Total Qauntity:- |  |  |  |  | Cft | 8.6111 |  |  | Sft | 68.8889
17 | Providing & laying of roof insulation comprising of single layer of Tile (9" x 4-1/4" x 1-1/2") grouted with cement sand morter 1:3 laid over 2" thich earth including mud plaster over polythine sheet of 500 gauge.
| Roof of both Toilet rooms | [6 empty] | 1 | 10.3333 | 6.6667 | 68.8889
| Total Qauntity:- | [8 empty] | Sft | 68.8889
18 | Providing and laying coping of 1.5 inch (40mm) thick machine mixed 1:2:4 cement concrete using graded crushed boulders 3/4 inch (19mm) and down gauge in ground floor laid in panels including form work, consolidation, finishing, curing etc., complete
|  | L/W | [5 empty] | 2 | 10.3333 | 0.75 | 15.5
|  | S/W | [5 empty] | 2 | 6.6667 | 0.75 | 10
| Total Qauntity:- | [8 empty] | Sft | 25.5

## site plan
Housing Urban Development & Public Health Engineering Department Division Faisalabad
Government Boy's High School 58/JB UC 177 District Faisalabad
Scope of work (detail & specs are in BOQs)
1- 8 no of wash basins
2- 9 no of Flush tanks in existing toilets
3-Distemper work
4- Weather shield
Main Gate
3 room Toilet block
High Section
Ali Block
2 room Toilet block
Siddiq Block
3 room Toilet block

## Plan
Housing Urban Development & Public Health Engineering Department Division Faisalabad
Government Boy's High School 58/JB UC 177 District Faisalabad
Steel Door
Toilet Flush Tank (Master/Polo)
33-35 inches

## Sheet1
Housing Urban Development & Public Health Engineering Department Division Faisalabad
Desilting of floors/WC of two toilets, Provision 4 no of flush tanks, 4 no of wash basins, distemper, weather shield, raising of floors (2 toilet rooms),re-fixing of WCs , raising of roof (two toilets) and roof slabs with treatment
Government Boy's High School 58/JB UC 177 District Faisalabad
5.5'
|  |  | 9'' |  | 4.5'' |  |  | 4.5'' |  | 9''
|  | 8.1667 |  | 4' |  | 4' |  |  | 4'
| Raise of floors by 9''-1' | [9 empty] | Ground Level
14.25