## Tender
Housing Urban Development & Public Health Engineering Department Division Sahiwal
Government Boy's High School 97/6R UC 41 District Sahiwal
Desilting/cleaning of septic tanks 2 nos, Provision 9 no of flush tanks, 8 no of wash basins, distemper, weather shield, raising of floors (3 toilet rooms) and fixing of WCs
ABSTRACT OF QUANTITY & COST
Quantity/cost
Sr. | Description of work | Quantity | Unit | Unit Rate | Amount
1 | Providing & fitting of 8 number of wash basins medium size (master), connecting with existing water supply with stop cocks, single tape (steel) (sartaj/master), connection pipes (steel) strainer (jali) and waste pipe, fixing 10-15 feet pipe 4'' (Popular/Royal or similar quality) to disposing off waste water complete in all respect | 8 | Job
2 | Providing & fitting of flush tanks (master), connecting with existing water supply with stop cocks, (sartaj/master/Adam) connecting with pipe complete in all respect | 9 | Job
3 | Providing and applying Vinyl emulsion Dulux or berger paint, 2 coats including preparation of surface | 882 | Job
4 | Providing and applying weather sheild paint on exterior surface of building, including surface preparation and applying two coats | 558.125 | Job
5 | Providing and fixing 3'' Ф PVC pipe (Popular/Royal/equavelant quality) as drain of wash basin and septic tank (50 feet), fixing under ground at least 6'' deep in ground, 3'' PCC (1:2:4) mix over pipe as cover, | 1 | sft
6 | Dismeteling of concrete 1:2:4 (floors of toilets), | 30 | Job
7 | Transportation of earth all type when the total distance including the lead cover in the item is more then 1000 ft | 60 | cft
8 | Compaction of earthwork (soft, ordinary & hard soil), compaction by hand rammed in all respect | 60 | cft
9 | Dry rammed brick or stone ballast, 1½" to 2"( 40 mm to 50 mm) gauge. (3'' thick bottom layer ) | 30 | cft
10 | Providing and laying floor of 2 inch thick machine mixed 1:2:4 cement concrete using graded crushed boulders 3/4 inch (19 mm) and down gauge in ground floor laid in panels with marble dividers of 1/2"x2", consolidation, finishing, curing etc., complete | 60 | cft
11 | Providing and fitting indian water closet (WC) large size, Master, pole, 3 star or equavelent with 3'' Ф P-Trap, stop cock, connection pipe, J-pipe (connect with flush tank) complete in all respect | 3 | sft
Sub Total

## Measurements
Housing Urban Development & Public Health Engineering Department Division Sahiwal
Government Boy's High School 97/6R UC 41 District Sahiwal
Desilting/cleaning of septic tanks 2 nos, Provision 9 no of flush tanks, 8 no of wash basins, distemper, weather shield, raising of floors (3 toilet rooms) and fixing of WCs
MEASUREMENTS
Sr. No. | Description |  | CFT Measurements |  |  |  |  | SFT Measurements
|  |  | Nos. | Length (FT) | Width (FT) D2 | Depth (FT) H | Volume (CFT) (DxExFxG) | Nos. | Length (FT) | Width (FT) | Area (SFT) (I*J*K=L)
1 | Providing & fitting of 8 number of wash basins medium size (master), connecting with existing water supply with stop cocks, single tape (steel) (sartaj/master), connection pipes (steel) strainer (jali) and waste pipe, fixing 10-15 feet pipe 4'' (Popular/Royal or similar quality) to disposing off waste water complete in all respect
| Near Siddiq Block | [9 empty] | 3
| Near ali Block | [9 empty] | 3
| Near XX Block | [9 empty] | 2
| Total Qauntity:- | [8 empty] | Job | 8
2 | Providing & fitting of flush tanks (master), connecting with existing water supply with stop cocks, (sartaj/master/Adam) connecting with pipe complete in all respect
| Near Siddiq Block | [9 empty] | 3
| Near ali Block | [9 empty] | 3
| Near XX Block | [9 empty] | 3
| Total Qauntity:- | [8 empty] | Job | 9
3 | Providing and applying Vinyl emulsion Dulux or berger paint, 2 coats including preparation of surface
|  | L/W | [5 empty] | 6 | 5 | 8.1667 | 245
|  | S/W | [5 empty] | 6 | 4 | 8.1667 | 196
| Sub Total:- | [8 empty] | Sft | 441
| Total Qauntity:- (2 coats) | [8 empty] | Sft | 882
4 | Providing and applying weather sheild paint on exterior surface of building, including surface preparation and applying two coats
| Below DPC | L/W | [5 empty] | 1 | 17.25 | 1.5 | 25.875
|  | S/W | [5 empty] | 1 | 6.5 | 1.5 | 9.75
| Above DPC | L/W | [5 empty] | 1 | 17.25 | 10.25 | 176.8125
|  | S/W | [5 empty] | 1 | 6.5 | 10.25 | 66.625
| Sub Total:- | [9 empty] | 279.0625
| Total Qauntity:- (2 coats) | [8 empty] | Sft | 558.125
5 | Providing and fixing 3'' Ф PVC pipe (Popular/Royal/equavelant quality) as drain of wash basin and septic tank (50 feet), fixing under ground at least 6'' deep in ground, 3'' PCC (1:2:4) mix over pipe as cover, | [8 empty] | Job | 1
6 | Dismeteling of concrete 1:2:4 (floors of toilets),
| three no of floor (5'x4') |  | 3 | 5 | 4 | 0.5 | 30
| Total Quantity:- | [5 empty] | 30
7 | Transportation of earth all type when the total distance including the lead cover in the item is more then 1000 ft
| Providing earth for filling under floors of toilets (5'x'4') |  | 3 | 5 | 4 | 0.75 | 60
| Total Qauntity:- | [5 empty] | 60
8 | Compaction of earthwork (soft, ordinary & hard soil), compaction by hand rammed in all respect
| Total Qauntity:- (Qty as per item No-2) | [5 empty] | 60
9 | Dry rammed brick or stone ballast, 1½" to 2"( 40 mm to 50 mm) gauge. (3'' thick bottom layer )
| under floors of toilets |  | 3 | 5 | 4 | 0.5 | 30
| Total Quantity:- (in Cft) |  |  |  |  | Cft | 30
10 | Providing and laying floor of 2 inch thick machine mixed 1:2:4 cement concrete using graded crushed boulders 3/4 inch (19 mm) and down gauge in ground floor laid in panels with marble dividers of 1/2"x2", consolidation, finishing, curing etc., complete
| Toilet (5'x4') | [6 empty] | 3 | 5 | 4 | 60
| Total Quantity:- (in sft) | [8 empty] | Sft | 60
11 | Providing and fitting indian water closet (WC) large size, Master, pole, 3 star or equavelent with 3'' Ф P-Trap, stop cock, connection pipe, J-pipe (connect with flush tank) complete in all respect | [8 empty] | No | 3

## site plan
Housing Urban Development & Public Health Engineering Department Division Sahiwal
Government Boy's High School 97/6R UC 41 District Sahiwal
Scope of work (detail & specs are in BOQs)
1- 8 no of wash basins
2- 9 no of Flush tanks in existing toilets
3-Distemper work
4- Weather shield
Main Gate
3 room Toilet block
High Section
Ali Block
2 room Toilet block
Siddiq Block
3 room Toilet block

## Plan
Housing Urban Development & Public Health Engineering Department Division Sahiwal
Government Boy's High School 97/6R UC 41 District Sahiwal
Steel Door
Toilet Flush Tank (Master/Polo)
33-35 inches

## Sheet1
Housing Urban Development & Public Health Engineering Department Division Sahiwal
Desilting/cleaning of septic tanks 2 nos, Provision 9 no of flush tanks, 8 no of wash basins, distemper, weather shield, raising of floors (3 toilet rooms) and fixing of WCs
Government Boy's High School 97/6R UC 41 District Sahiwal
5.5'
|  |  | 9'' |  | 4.5'' |  |  | 4.5'' |  | 9''
|  | 8.1667 |  | 4' |  | 4' |  |  | 4'
| Raise of floors by 9''-1' | [9 empty] | Ground Level
14.25